## Defect Data
Test Lead | Why defect was not identified during testing? | Are related requirements recorded in the BR or UCS? | If prior response is "Yes", list down the BR or UCS document number(s) and clause identifier(s) | Primary Root Cause Classification #3 | Remark | Proposed solution to prevent recurrence
Esther Ong | Test case wrongly tested for "different tiers" requirement due to misinterpretation. | Yes | L1081 | Ambiguous Requirement [SA]
Esther Ong | Test case worked but for the wrong requirement. | No |  | Ambiguous Requirement [SA]
Phoon CF | Test case worked but was not for the intended requirement. | No |  | Ambiguous Requirement [SA]
Jessie Chua | Test case failed to implement "normal fare" requirement. | Yes | SYS | Ambiguous Requirement [SA]
Phoon CF | Requirement given was tested but interpreted wrongly. | No |  | Ambiguous Requirement [SA]
Esther Ong | Test case failed to consider edge cases of ambiguous requirement given. | No |  | Ambiguous Requirement [SA]
Jessie Chua | Test case worked but was not the intended functionality stated in the requirements. | No |  | Ambiguous Requirement [SA]
Phoon CF | "Peak periods" was not clearly stated. | No |  | Ambiguous Requirement [SA]
Phoon CF | Tests for "special timings" had loop holes due to different understanding of it. | Yes | BRUL | Ambiguous Requirement [SA]
Jessie Chua | Tests did not account for the new data structures due to the unclear time frame. | Yes | L1081 | Ambiguous Requirement [SA]
Esther Ong | Tests did not consider the data types from connecting system because it was not clearly stated. | No |  | Ambiguous Requirement [SA]
Jessie Chua | Not all user interfaces were tested because the project was assumed to only be customer facing. | No |  | Ambiguous Requirement [SA]
Phoon CF | Interaction with user facing system was not expected. | No |  | Ambiguous Requirement [SA]
Phoon CF | Tests did not test if the new function is compatible to student fare because it was not clearly stated in the system requirements. | No |  | Ambiguous Requirement [SA]
Esther Ong | Compatibility with old data structures were not tested because it was thought to be not important. | No |  | Ambiguous Requirement [SA]
Jessie Chua | Compatibility with old data structures were not tested because it was thought to be not useful in this project. | No |  | Ambiguous Requirement [SA]
Phoon CF | Test case did not consider the effects of the verification process. | No |  | Ambiguous Requirement [SA]
Phoon CF | Test case did not consider the effects of the new fares updating process. | No |  | Ambiguous Requirement [SA]
Jessie Chua | The test did not consider limitations of the desktop version. | No |  | Ambiguous Requirement [SA]
Phoon CF | Test case did not check the new user inferface design on station computers. | No |  | Ambiguous Requirement [SA]
Jessie Chua | Test did not check if the system architecture can interact with the old user interface. | No |  | Ambiguous Requirement [SA]
Phoon CF | Business requirement given was open to interpretation. | No |  | Ambiguous Requirement [BR]
Jessie Chua | Requirement given by business team was not clear. | Yes | SYS | Ambiguous Requirement [BR]
Phoon CF | Business requirement was not specific enough. | Yes | SYS | Ambiguous Requirement [BR]
Esther Ong | Requirement of "more efficient" was not specific. | Yes | SYS | Ambiguous Requirement [BR]
| "More efficient" requirement was interpreted in a different way. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not test 'Help'button on app because it was not stated if the app had to be improved too. | No |  | Ambiguous Requirement [BR]
Jessie Chua | Test case did not test station tracking functions because it was thought to be excluded from the maintenance. | No |  | Ambiguous Requirement [BR]
Esther Ong | Test case did not account for the right time period because requirement only stated 'when appropriate'. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not account for the right fare rates because requirement only stated 'when necessary'. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not test for difference in colour matches because 'better usability' requirement was not specific enough. | No |  | Ambiguous Requirement [BR]
Esther Ong | Test case did not work for 'low traffic periods' because it was clearly defined. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not take into account station team work processes because 'better workflow' was not clear. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not take into account fare changes in the long run. | No |  | Ambiguous Requirement [BR]
Esther Ong | Test case did not test for different languages because the meaning of "better usability" was not clear. | No |  | Ambiguous Requirement [BR]
Jessie Chua | Test case did not test secondary features because it was not considered to be part of the 'main system'. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not account for 'high traffic periods' because it was clearly defined. | No |  | Ambiguous Requirement [BR]
Jessie Chua | Test case did not account for the right users because requirement only stated 'when appropriate'. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not test for office users because "all necessary users" was vague. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not account for differences in office and station work processes because 'improve overall workflow' was not clear. | No |  | Ambiguous Requirement [BR]
Phoon CF | Test case did not test for the right users because requirement only stated 'when appropriate'. | No |  | Ambiguous Requirement [BR]
Jessie Chua | Test case did not take into account all passenger types because requirement only stated 'if needed'. | No |  | Ambiguous Requirement [BR]
Phoon CF | Connection to intranet but not office network was not tested because it was not specified. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case did not consider new data struture because it was assumed to not matter. | No |  | Ambiguous Requirement [Software]
Esther Ong | Test case failed to take into account the specific data structure from incoming system. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case did not test for the right data structure because "suitable" requirement was vague. | No |  | Ambiguous Requirement [Software]
Jessie Chua | Test case did not test for comaptibility with old data structure because it was thought to be out of use. | Yes | L1081 | Ambiguous Requirement [Software]
Phoon CF | Test case did not test for temporary employees user access. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case did not consider non station employee user access. | Yes | BRUL | Ambiguous Requirement [Software]
Esther Ong | Test case did not take into account office employee user acess. | Yes | BRUL | Ambiguous Requirement [Software]
Jessie Chua | Test case did not test compatibility with new app. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case failed to account for software updates. | Yes | L1081 | Ambiguous Requirement [Software]
Phoon CF | Test case failed to test connection with reporting system. | No |  | Ambiguous Requirement [Software]
Esther Ong | Test case did not consider interaction with new fare calculation system. | No |  | Ambiguous Requirement [Software]
Jessie Chua | Test case did not consider effects of software updates. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case did not consider compatibility with old database. | No |  | Ambiguous Requirement [Software]
Jessie Chua | Test case failed to intake data from old support software. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case did not block previous employee user access. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case failed to take into consideration the effect of old data structures. | No |  | Ambiguous Requirement [Software]
Esther Ong | Test case failed to connect to station employee software. | No |  | Ambiguous Requirement [Software]
Jessie Chua | Test case did not consider the effects of legacy software. | No |  | Ambiguous Requirement [Software]
Esther Ong | Test case did not test for comaptibility with old data structures. | No |  | Ambiguous Requirement [Software]
Phoon CF | Test case did not take into account how new software updates can affect the new feature. | No |  | Ambiguous Requirement [Software]
Jessie Chua | This requirement was not included in the business document. | No |  | Missing Requirement [BR]
Phoon CF | This requirement was not mentioned in the business document. | No |  | Missing Requirement [BR]
Phoon CF | This requirement was not stated in the business document. | No |  | Missing Requirement [BR]
Jessie Chua | This requirement was not specified in the business document. | No |  | Missing Requirement [BR]
Esther Ong | This requirement was not recorded by the business analysts. | No |  | Missing Requirement [BR]
Phoon CF | This requirement was not given by the business analysts. | No |  | Missing Requirement [BR]
Jessie Chua | This requirement was not passed on from the business analysts. | No |  | Missing Requirement [BR]
Esther Ong | The business analysts did not pass on this requirement. | No |  | Missing Requirement [BR]
Phoon CF | The business analysts did not document this requirement. | Yes | SYS | Missing Requirement [BR]
Jessie Chua | The business analysts did not include this requirement. | No |  | Missing Requirement [BR]
Jessie Chua | The business document did not contain this requirement. | Yes | BRUL | Missing Requirement [BR]
Phoon CF | The business document did not state this requirement. | No |  | Missing Requirement [BR]
Esther Ong | The business document did not mention this requirement. | Yes | BRUL | Missing Requirement [BR]
Jessie Chua | The business document did not specify this requirement. | Yes | L1081 | Missing Requirement [BR]
Phoon CF | This requirement was missing from the business document. | No |  | Missing Requirement [BR]
Jessie Chua | This requirement was not stated in the business document. | Yes | BRUL | Missing Requirement [BR]
Esther Ong | This requirement was not found in the business document. | No |  | Missing Requirement [BR]
Phoon CF | The business document did not have this requirement. | No |  | Missing Requirement [BR]
Jessie Chua | This requirement was not recorded in the business document. | No |  | Missing Requirement [BR]
Phoon CF | This requirement was not in the business document. | Yes |  | Missing Requirement [BR]
Phoon CF | This requirement was not stated in the business document. | No |  | Missing Requirement [BR]
Jessie Chua | This requirement was not recorded by the design team. | No |  | Missing Requirement [SA]
Phoon CF | This requirement was not given by the design team. | No |  | Missing Requirement [SA]
Esther Ong | This requirement was not passed on from the design team. | No |  | Missing Requirement [SA]
Phoon CF | The design team did not pass on this requirement. | No |  | Missing Requirement [SA]
Jessie Chua | The design team did not document this requirement. | No |  | Missing Requirement [SA]
Jessie Chua | The design team did not include this requirement. | No |  | Missing Requirement [SA]
Phoon CF | This system level design requirement was not documented. | No |  | Missing Requirement [SA]
Jessie Chua | This system level design requirement was not given. | No |  | Missing Requirement [SA]
Phoon CF | This system level design requirement was not mentioned. | Yes | L1081 | Missing Requirement [SA]
Jessie Chua | This system level design requirement was not specified. | Yes | BRUL | Missing Requirement [SA]
Phoon CF | This system level design requirement was not given by the design team. | Yes | BRUL | Missing Requirement [SA]
Phoon CF | The design team did not mention this requirement. | Yes | L1081 | Missing Requirement [SA]
Esther Ong | The design team did not specify this requirement. | Yes | L1081 | Missing Requirement [SA]
Esther Ong | This requirement was not specified by the design team. | Yes | SYS | Missing Requirement [SA]
Phoon CF | This system level design requirement was missing. | Yes | BRUL | Missing Requirement [SA]
Jessie Chua | The design team did not pass along this requirement. | Yes | L1081 | Missing Requirement [SA]
Esther Ong | The design team misssed out this requirement. | Yes | L1081 | Missing Requirement [SA]
Phoon CF | This system level design requirement was not specified. | Yes | SYS | Missing Requirement [SA]
Phoon CF | The design team left out this requirement. | Yes | SYS | Missing Requirement [SA]
Jessie Chua | This system level design requirement was not specified by the design team. | No |  | Missing Requirement [SA]
Phoon CF | This requirement was not stated by the design team. | No |  | Missing Requirement [SA]
Jessie Chua | This software requirement was not included. | No |  | Missing Requirement [Software]
Esther Ong | This software requirement was not mentioned. | No |  | Missing Requirement [Software]
Phoon CF | This software requirement was not stated. | No |  | Missing Requirement [Software]
Esther Ong | This software requirement was not specified. | No |  | Missing Requirement [Software]
Phoon CF | This software requirement was missing. | No |  | Missing Requirement [Software]
Phoon CF | This software requirement was not documented. | No |  | Missing Requirement [Software]
Esther Ong | This software requirement was not given. | No |  | Missing Requirement [Software]
Jessie Chua | This software requirement was not made known to testers. | No |  | Missing Requirement [Software]
Phoon CF | There was no such software requirement stated. | No |  | Missing Requirement [Software]
Jessie Chua | There was no such software requirement mentioned. | No |  | Missing Requirement [Software]
Phoon CF | There was no such software requirement specified. | No |  | Missing Requirement [Software]
Phoon CF | There was no such software requirement given. | No |  | Missing Requirement [Software]
Esther Ong | There was no such software requirement documented. | No |  | Missing Requirement [Software]
Phoon CF | There was no such software requirement. | No |  | Missing Requirement [Software]
Jessie Chua | This software requirement did not exist before. | No |  | Missing Requirement [Software]
Phoon CF | This software requirement did not exist. | No |  | Missing Requirement [Software]
Jessie Chua | This software requirement was missing. | No |  | Missing Requirement [Software]
Phoon CF | This software requirement was not mentioned. | No |  | Missing Requirement [Software]
Esther Ong | This software requirement was not included. | No |  | Missing Requirement [Software]
Esther Ong | This software requirement was missing. | No |  | Missing Requirement [Software]
Esther Ong | This software requirement was not given. | No |  | Missing Requirement [Software]
Jessie Chua | Test cases was not chosen based on the impact analysis. | No |  | Missing Test Case
Esther Ong | Test case not performed. | No |  | Missing Test Case
Phoon CF | Test case not executed. | No |  | Missing Test Case
Jessie Chua | Test cases was not chosen based on impact analysis. | No |  | Missing Test Case
Phoon CF | Test cases was not chosen based on the impact analysis. | No |  | Missing Test Case
Esther Ong | Test case was not performed. | No |  | Missing Test Case
Phoon CF | Test case was not executed. | No |  | Missing Test Case
Phoon CF | Test case was not chosen based on impact analysis. | No |  | Missing Test Case
Jessie Chua | Based on impact analysis, this test case was not chosen. | No |  | Missing Test Case
Phoon CF | Test case was not chosen based on the impact analysis. | No |  | Missing Test Case
Esther Ong | Test case not performed. | No |  | Missing Test Case
Phoon CF | Test case was not executed. | No |  | Missing Test Case
Jessie Chua | Test case was not chosen based on the impact analysis. | No |  | Missing Test Case
Phoon CF | Test case was not executed. | No |  | Missing Test Case
Esther Ong | Test case not performed. | No |  | Missing Test Case
Phoon CF | Test case was not chosen based on the impact analysis. | No |  | Missing Test Case
Phoon CF | Test case was not executed. | No |  | Missing Test Case
Esther Ong | Test case not performed. | No |  | Missing Test Case
Phoon CF | Test case not performed. | No |  | Missing Test Case
Jessie Chua | Test case was not chosen based on the impact analysis. | No |  | Missing Test Case
Esther Ong | Test case was not chosen based on the impact analysis. | No |  | Missing Test Case
Jessie Chua | This is outside the scope of the project. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the function. | No |  | Not Within Scope
Esther Ong | This is outside the scope of the features. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the tests. | No |  | Not Within Scope
Jessie Chua | This is outside the scope of the features. | No |  | Not Within Scope
Esther Ong | This is outside the scope of the function. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the tests. | No |  | Not Within Scope
Jessie Chua | This is outside the scope of the project. | No |  | Not Within Scope
Jessie Chua | This is outside the scope of the features. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the function. | No |  | Not Within Scope
Esther Ong | This is out of scope. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the project. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the function. | No |  | Not Within Scope
Jessie Chua | This is out of scope. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the features. | No |  | Not Within Scope
Esther Ong | This is outside the scope of the tests. | No |  | Not Within Scope
Phoon CF | This is out of scope. | No |  | Not Within Scope
Esther Ong | This is outside the scope of the project. | No |  | Not Within Scope
Jessie Chua | This is outside the scope of the tests. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the function. | No |  | Not Within Scope
Phoon CF | This is outside the scope of the features. | No |  | Not Within Scope
Jessie Chua | This issue is specific to production envrionment only. | No |  | Test & Production Environment Difference
Phoon CF | This issue is specific to production only. | No |  | Test & Production Environment Difference
Esther Ong | This was not an issue in the Test Lab. | No |  | Test & Production Environment Difference
Phoon CF | This aspect of production environment was not replicated in the Test Lab. | No |  | Test & Production Environment Difference
Jessie Chua | Test Lab could not replicate this production environment feature. | No |  | Test & Production Environment Difference
Phoon CF | Test Lab could not replicate this production environment aspect. | No |  | Test & Production Environment Difference
Jessie Chua | This aspect of production environment cannot be replicated in the Test Lab. | No |  | Test & Production Environment Difference
Phoon CF | Not possible to replicate this issue in the Test Lab. | No |  | Test & Production Environment Difference
Esther Ong | Unable to test this in the Test Lab. | No |  | Test & Production Environment Difference
Phoon CF | Not possible to test this in the Test Lab. | No |  | Test & Production Environment Difference
Jessie Chua | This was not an issue in the Test Lab. | No |  | Test & Production Environment Difference
Phoon CF | Test Lab could not replicate this specific issue. | No |  | Test & Production Environment Difference
Jessie Chua | This issue applies only to the production envrionment. | No |  | Test & Production Environment Difference
Phoon CF | Unable to replicate this issue in the Test Lab. | No |  | Test & Production Environment Difference
Esther Ong | This was not an issue in the Test Lab. | No |  | Test & Production Environment Difference
Jessie Chua | This issue is specific to production envrionment. | No |  | Test & Production Environment Difference
Phoon CF | Issue was not observed in the Test Lab. | No |  | Test & Production Environment Difference
Jessie Chua | This issue is specific to production only. | Yes | BRUL | Test & Production Environment Difference
Phoon CF | This issue applies only to the production envrionment. | No |  | Test & Production Environment Difference
Esther Ong | Issue was not observed in the Test Lab. | Yes | BRUL | Test & Production Environment Difference
Phoon CF | This issue applies only to the production envrionment. | No |  | Test & Production Environment Difference
Jessie Chua | This was not an issue in the Test Lab. | Yes | L1081 | Test & Production Environment Difference
Esther Ong | Production environment has a different operating procedure. | No |  | Test & Production Operation Difference
Phoon CF | Production operating procedure cannot be replicated in Test Lab. | No |  | Test & Production Operation Difference
Jessie Chua | Test lab cannot replicate this operating process from production. | Yes | SYS | Test & Production Operation Difference
Phoon CF | Issue cannot be replicated in Test Lab due to different operations. | No |  | Test & Production Operation Difference
Phoon CF | Issue cannot be replicated in Test Lab because of different operation procedures. | No |  | Test & Production Operation Difference
Esther Ong | Issue cannot be replicated in Test Lab because of different operations. | No |  | Test & Production Operation Difference
Jessie Chua | Test Lab cannot reproduce this production operation specific issue. | No |  | Test & Production Operation Difference
Phoon CF | This issue is specific to production operations. | No |  | Test & Production Operation Difference
Jessie Chua | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Phoon CF | Issue cannot be replicated in Test Lab because of different operations. | No |  | Test & Production Operation Difference
Phoon CF | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Esther Ong | This issue is specific to production operations. | No |  | Test & Production Operation Difference
Esther Ong | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Jessie Chua | Production environment has a different operating procedure. | No |  | Test & Production Operation Difference
Phoon CF | Test Lab cannot reproduce this issue specific to production operations. | No |  | Test & Production Operation Difference
Jessie Chua | This poduction operating procedure cannot be replicated in Test Lab. | No |  | Test & Production Operation Difference
Esther Ong | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Phoon CF | Issue cannot be replicated in Test Lab because of different operations. | No |  | Test & Production Operation Difference
Esther Ong | This issue is specific to production operations. | No |  | Test & Production Operation Difference
Phoon CF | This poduction operating procedure cannot be replicated in Test Lab. | No |  | Test & Production Operation Difference
Esther Ong | Test Lab cannot reproduce this issue specific to production operations. | No |  | Test & Production Operation Difference
Jessie Chua | Production environment has a different operating procedure. | No |  | Test & Production Operation Difference
Phoon CF | Issue cannot be replicated in Test Lab because of different operations. | No |  | Test & Production Operation Difference
Phoon CF | This poduction operating procedure cannot be replicated in Test Lab. | No |  | Test & Production Operation Difference
Esther Ong | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Jessie Chua | Test Lab cannot reproduce this issue specific to production operations. | No |  | Test & Production Operation Difference
Esther Ong | Issue cannot be replicated in Test Lab because of different operations. | No |  | Test & Production Operation Difference
Phoon CF | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Esther Ong | Test Lab cannot reproduce this issue specific to production operations. | No |  | Test & Production Operation Difference
Phoon CF | This poduction operating procedure cannot be replicated in Test Lab. | No |  | Test & Production Operation Difference
Esther Ong | This issue applies only to production operations. | No |  | Test & Production Operation Difference
Jessie Chua | Issue cannot be replicated in Test Lab because of different operations. | No |  | Test & Production Operation Difference
Phoon CF | Not enough time to test this issue. | No |  | Time Constraint
Jessie Chua | Issue was not tested due to limited time. | No |  | Time Constraint
Phoon CF | Timeline was too tight to test this issue. | No |  | Time Constraint
Esther Ong | This issue was left out of testing due to limited time. | No |  | Time Constraint
Phoon CF | Issue was not tested due to time constraint. | No |  | Time Constraint
Esther Ong | Timeline was too short to test this issue. | No |  | Time Constraint
Esther Ong | Left out due to time constraint. | No |  | Time Constraint
Phoon CF | Left out due to limited time. | No |  | Time Constraint
Esther Ong | Timeline was too tight. | No |  | Time Constraint
Phoon CF | Not enough time. | No |  | Time Constraint
Phoon CF | Time was too short to fully test this issue. | No |  | Time Constraint
Esther Ong | Not enough time given to fully test this issue. | No |  | Time Constraint
Phoon CF | More time is needed to fully test this issue. | No |  | Time Constraint
Esther Ong | Issue cannot be tested in such a short time period. | No |  | Time Constraint
Phoon CF | Issue can only be assessed in a longer time period. | No |  | Time Constraint
Jessie Chua | Issue can only be evaluated in a longer time period. | No |  | Time Constraint
Phoon CF | More time is needed to test this issue. | No |  | Time Constraint
Esther Ong | More time needed to check this issue. | No |  | Time Constraint
Phoon CF | Did not test this issue due to time constraint. | No |  | Time Constraint
Jessie Chua | Not enough time to test this issue. | Yes | L1081 | Time Constraint
Phoon CF | More time needed to test this issue. | Yes | L1081 | Time Constraint
Esther Ong | Issue was not tested due to limited time. | Yes | BRUL | Time Constraint
Phoon CF | More time should be given to test this issue. | Yes | SYS | Time Constraint

## Sheet1
Classification #3 | Why defect was not identified during testing
Ambiguous Requirement [SA] | Requirement given was tested but interpreted wrongly.
Ambiguous Requirement [BR] | Business requirement given was open to interpretation.
Ambiguous Requirement [Software] | Test case failed to account for software updates.
Missing Requirement [SA] | This requirement was not given by the design team.
Missing Requirement [BR] | This requirement was not specified in the business document.
Missing Requirement [Software] | This software requirement was not included.
Missing Test Case | Test case not performed.
Not Within Scope | This is outside the scope of the project.
Test & Production Environment Difference | Test case was not chosen based on the impact analysis.
Test & Production Operation Difference | This issue is specific to production operations.
Time Constraint | Issue was not tested due to time constraint.
Others | ?